## Read Me
Ridgeline Remodels Job Costing · Read Me
Topic | How to use this workbook
What this file is | A formula-only .xlsx workbook: no macros or VBA of any kind, so it opens in Excel without a security prompt. If you ever add macros yourself, save as .xlsm instead.
Workflow | 1) Keep Jobs, Cost Codes, and Employees current. 2) Estimate each job line by line on Estimates. 3) Capture actuals: crew time on Timesheets, materials and subcontractors on Cost Log. 4) Bill draws on Billings (NET 30). 5) Overhead pools office costs and sets one allocation rate. 6) WIP, Job P&L, and Utilization review themselves.
Entry rules | Enter dates as real dates (Mar 5, 2026). Amounts and hours are positive numbers in US dollars. Every timesheet line and every purchase carries one job number and one cost code; office time uses job OH and code 0000.
Cost codes first | The code list is the work breakdown structure shared by estimates, timesheets, and the cost log. Add a code once, then use it everywhere; the Estimates line check flags any code that is not on the list.
Labor burden | Loaded rate = base hourly rate x (1 + burden). The 25% burden models payroll taxes, workers comp, and benefits; adjust it per employee on the Employees sheet.
Overhead method | The pool (rent, trucks, insurance, office labor, and so on) is divided by direct costs to date to get one rate, then applied to each job in Job P&L column H. Change a pool amount and every job follows.
Progress billing | Draws follow NET 30 terms: due date = invoice date + 30 days. WIP compares earned revenue (contract x percent complete) with billed to date and flags any job that is out of step.
Sales tax | Amounts exclude sales tax. US sales-tax treatment of construction and services varies by state and by contract type -- confirm the treatment for your state with your state Department of Revenue before invoicing.
Subcontractors | Collect a completed W-9 from every subcontractor before the first payment, and track year-end 1099-NEC obligations. This workbook records costs only; it does not file information returns.
Not a contractor? | Agencies and consultants use the same skeleton: jobs become client engagements, cost codes become service lines (strategy, design, build), draws become monthly invoices, and Utilization becomes the billable ratio.
Capacity | Formulas aggregate rows 5 through 1004. The blank template pre-fills its formula columns down to row 204; beyond that, fill the formulas down further and extend every 5:1004 range to match.
Boundaries | Teaching model for a single-user small business: no multi-user permissions, approval workflow, audit log, or automatic backups. It is not a substitute for accounting software, a licensed accountant, or tax advice.

## Settings
Model Parameters
Parameter | Value | Notes
Period start | 46082 | Summaries and the pool include dates from this day (inclusive)
Period end | 46203 | Summaries and the pool include dates through this day (inclusive)
Report date | 46203 | Billings aging compares due dates against this day
Billing tolerance | 2500 | WIP flags a job when earned vs billed differs by more than this
Default labor burden | 25% | Payroll taxes, workers comp, benefits; loaded into Employees column G
Target gross margin | 15% | Job P&L flags any won job whose margin to date is below this
Credit terms | NET 30 | Due date = invoice date + 30 days (Billings column G)
Currency | USD | All amounts are US dollars, sales tax excluded

## Jobs
Jobs Master
Job # | Job Name | Client | Status | Contract Type | Start Date | Contract Price | Estimated Cost | Est Margin | Est GM %
J-2601 | Maple Kitchen Renovation | Daniel & Grace Hollis | Open | Fixed price | 2026-03-02 | 96250 | 77000 | 19250 | 20%
J-2602 | Cedar Deck Replacement | Ron & Jessie Marlowe | Open | Fixed price | 2026-04-06 | 20000 | 16100 | 3900 | 19.5%
J-2603 | Primary Bath Suite Remodel | Alicia Ferrell | Open | Fixed price | 2026-05-04 | 49000 | 39200 | 9800 | 20%
J-2604 | Garage Studio Conversion | Chris & Dana Okafor | Bid | Fixed price |  | 18600 | 15500 | 3100 | 16.67%
OH | Office & Admin (non-job) | Ridgeline Remodels LLC | Internal | Fixed price |  | 0 | 0

## Cost Codes
Cost Codes · Work Breakdown Structure
Code | Description | Cost Type | Typical Unit | Est Cost All Jobs | Notes
1000 | General Conditions | Other | LS | 7700 | Supervision, site setup, dumpster, cleaning
2100 | Demolition & Disposal | Subcontract | LS | 7900 | Demo and haul-off subcontract
2200 | Framing & Rough Carpentry | Labor | HR | 23300 | Crew framing and rough carpentry hours
2210 | Lumber & Framing Materials | Material | LOT | 13500 | Lumber, sheet goods, fasteners
2220 | Decking & Railing Materials | Material | SF | 6900 | Cedar decking, railing, hardware
3200 | Insulation | Subcontract | LS | 900 | Insulation subcontract
3300 | Drywall Labor | Subcontract | LS | 11600 | Hang, tape, and finish subcontract
3310 | Drywall Materials | Material | LOT | 2500 | Board, mud, tape, corner bead
3400 | Tile & Stone Labor | Subcontract | SF | 11100 | Tile setter subcontract
3410 | Tile & Stone Materials | Material | LOT | 4700 | Tile, setting materials, grout
5000 | Paint & Finishing | Subcontract | LS | 7400 | Painting and staining subcontract
6000 | Cabinetry & Counters | Material | LS | 18900 | Cabinet and countertop package
6100 | Electrical | Subcontract | LS | 17400 | Electrical subcontract
6200 | Plumbing | Subcontract | LS | 14000 | Plumbing subcontract
0000 | Office & Administration | Other | HR | 0 | Non-job time; excluded from job costs

## Employees
Crew & Loaded Labor Rates
Code | Name | Role | Base Rate | Burden % | Loaded Rate | Notes
E01 | Dana Whitfield | Owner & Project Lead | 48 | 25% | 60 | Supervision logged to cost code 1000
E02 | Marcus Reed | Lead Carpenter | 36 | 25% | 45 | Full-time on production work
E03 | Sofia Nguyen | Carpenter | 32 | 25% | 40 | Full-time on production work
E04 | Tyler Brooks | Apprentice | 20 | 25% | 25 | Second-year apprentice
E05 | Priya Patel | Office & Bookkeeping | 24 | 25% | 30 | Non-job time logged to job OH
E06 | Jamal Wright | Laborer & Site Support | 28 | 25% | 35 | Site cleanup, deliveries, help

## Estimates
Estimate vs Actual by Job and Cost Code
Job # | Cost Code | Description | Cost Type | Est Cost | Actual Labor | Actual Non-Labor | Actual Total | Variance | % of Est Used | Check
J-2601 | 1000 | General Conditions | Other | 4800 | 640 | 0 | 640 | -4160 | 13.33% | OK
J-2601 | 2100 | Demolition & Disposal | Subcontract | 3900 | 0 | 4150 | 4150 | 250 | 106.4% | OK
J-2601 | 2200 | Framing & Rough Carpentry | Labor | 9600 | 2240 | 0 | 2240 | -7360 | 23.33% | OK
J-2601 | 2210 | Lumber & Framing Materials | Material | 7200 | 0 | 6890 | 6890 | -310 | 95.69% | OK
J-2601 | 6100 | Electrical | Subcontract | 8400 | 0 | 8275 | 8275 | -125 | 98.51% | OK
J-2601 | 6200 | Plumbing | Subcontract | 6700 | 0 | 7120 | 7120 | 420 | 106.3% | OK
J-2601 | 3300 | Drywall Labor | Subcontract | 5600 | 0 | 5940 | 5940 | 340 | 106.1% | OK
J-2601 | 3310 | Drywall Materials | Material | 1700 | 0 | 1760 | 1760 | 60 | 103.5% | OK
J-2601 | 6000 | Cabinetry & Counters | Material | 18900 | 0 | 19450 | 19450 | 550 | 102.9% | OK
J-2601 | 3400 | Tile & Stone Labor | Subcontract | 4300 | 0 | 4265 | 4265 | -35 | 99.19% | OK
J-2601 | 3410 | Tile & Stone Materials | Material | 2100 | 0 | 2070 | 2070 | -30 | 98.57% | OK
J-2601 | 5000 | Paint & Finishing | Subcontract | 3800 | 0 | 3690 | 3690 | -110 | 97.11% | OK
J-2602 | 2100 | Demolition & Disposal | Subcontract | 1600 | 0 | 1485 | 1485 | -115 | 92.81% | OK
J-2602 | 2200 | Framing & Rough Carpentry | Labor | 4800 | 1300 | 0 | 1300 | -3500 | 27.08% | OK
J-2602 | 2210 | Lumber & Framing Materials | Material | 1400 | 0 | 1240 | 1240 | -160 | 88.57% | OK
J-2602 | 2220 | Decking & Railing Materials | Material | 6900 | 0 | 7310 | 7310 | 410 | 105.9% | OK
J-2602 | 5000 | Paint & Finishing | Subcontract | 1400 | 0 | 1655 | 1655 | 255 | 118.2% | OK
J-2603 | 1000 | General Conditions | Other | 2900 | 580 | 0 | 580 | -2320 | 20% | OK
J-2603 | 2100 | Demolition & Disposal | Subcontract | 2400 | 0 | 2290 | 2290 | -110 | 95.42% | OK
J-2603 | 2200 | Framing & Rough Carpentry | Labor | 3700 | 800 | 0 | 800 | -2900 | 21.62% | OK
J-2603 | 2210 | Lumber & Framing Materials | Material | 1600 | 0 | 1530 | 1530 | -70 | 95.62% | OK
J-2603 | 3200 | Insulation | Subcontract | 900 | 0 | 940 | 940 | 40 | 104.4% | OK
J-2603 | 3300 | Drywall Labor | Subcontract | 3100 | 0 | 3080 | 3080 | -20 | 99.35% | OK
J-2603 | 3310 | Drywall Materials | Material | 800 | 0 | 745 | 745 | -55 | 93.12% | OK
J-2603 | 3400 | Tile & Stone Labor | Subcontract | 6800 | 0 | 6970 | 6970 | 170 | 102.5% | OK
J-2603 | 3410 | Tile & Stone Materials | Material | 2600 | 0 | 0 | 0 | -2600 | 0% | OK
J-2603 | 6100 | Electrical | Subcontract | 4900 | 0 | 4760 | 4760 | -140 | 97.14% | OK
J-2603 | 6200 | Plumbing | Subcontract | 7300 | 0 | 7480 | 7480 | 180 | 102.5% | OK
J-2603 | 5000 | Paint & Finishing | Subcontract | 2200 | 0 | 0 | 0 | -2200 | 0% | OK
J-2604 | 2200 | Framing & Rough Carpentry | Labor | 5200 | 0 | 0 | 0 | -5200 | 0% | OK
J-2604 | 2210 | Lumber & Framing Materials | Material | 3300 | 0 | 0 | 0 | -3300 | 0% | OK
J-2604 | 6100 | Electrical | Subcontract | 4100 | 0 | 0 | 0 | -4100 | 0% | OK
J-2604 | 3300 | Drywall Labor | Subcontract | 2900 | 0 | 0 | 0 | -2900 | 0% | OK

## Timesheets
Timesheets (Employee x Job x Cost Code)
Entry # | Date | Employee Code | Employee | Job # | Cost Code | Hours | Loaded Rate | Labor Cost
TS-1001 | 2026-03-05 | E02 | Marcus Reed | J-2601 | 2200 | 8 | 45 | 360
TS-1002 | 2026-03-05 | E03 | Sofia Nguyen | J-2601 | 2200 | 8 | 40 | 320
TS-1003 | 2026-03-06 | E04 | Tyler Brooks | J-2601 | 2200 | 8 | 25 | 200
TS-1004 | 2026-03-12 | E01 | Dana Whitfield | J-2601 | 1000 | 6 | 60 | 360
TS-1005 | 2026-03-19 | E03 | Sofia Nguyen | J-2601 | 2200 | 8 | 40 | 320
TS-1006 | 2026-03-20 | E02 | Marcus Reed | J-2601 | 2200 | 8 | 45 | 360
TS-1007 | 2026-04-02 | E02 | Marcus Reed | J-2601 | 2200 | 8 | 45 | 360
TS-1008 | 2026-04-02 | E06 | Jamal Wright | J-2601 | 1000 | 8 | 35 | 280
TS-1009 | 2026-04-16 | E03 | Sofia Nguyen | J-2601 | 2200 | 8 | 40 | 320
TS-1010 | 2026-04-08 | E02 | Marcus Reed | J-2602 | 2200 | 8 | 45 | 360
TS-1011 | 2026-04-09 | E03 | Sofia Nguyen | J-2602 | 2200 | 7 | 40 | 280
TS-1012 | 2026-04-15 | E04 | Tyler Brooks | J-2602 | 2200 | 8 | 25 | 200
TS-1013 | 2026-04-23 | E06 | Jamal Wright | J-2602 | 2200 | 8 | 35 | 280
TS-1014 | 2026-05-14 | E02 | Marcus Reed | J-2602 | 2200 | 4 | 45 | 180
TS-1015 | 2026-05-06 | E02 | Marcus Reed | J-2603 | 2200 | 8 | 45 | 360
TS-1016 | 2026-05-07 | E03 | Sofia Nguyen | J-2603 | 2200 | 6 | 40 | 240
TS-1017 | 2026-05-20 | E04 | Tyler Brooks | J-2603 | 2200 | 8 | 25 | 200
TS-1018 | 2026-06-03 | E01 | Dana Whitfield | J-2603 | 1000 | 5 | 60 | 300
TS-1019 | 2026-06-10 | E06 | Jamal Wright | J-2603 | 1000 | 8 | 35 | 280
TS-1020 | 2026-03-31 | E05 | Priya Patel | OH | 0000 | 8 | 30 | 240
TS-1021 | 2026-04-30 | E05 | Priya Patel | OH | 0000 | 8 | 30 | 240
TS-1022 | 2026-05-29 | E05 | Priya Patel | OH | 0000 | 8 | 30 | 240
TS-1023 | 2026-06-30 | E05 | Priya Patel | OH | 0000 | 8 | 30 | 240

## Cost Log
Material & Subcontractor Log
Entry # | Date | Job # | Cost Code | Cost Type | Vendor / Payee | Description | Amount
CM-101 | 2026-03-09 | J-2601 | 2100 | Subcontract | Carder Demolition LLC | Kitchen demo and haul-off | 4150
CM-102 | 2026-03-20 | J-2601 | 2210 | Material | Northgate Lumber Co | Framing package: lumber, sheet goods, fasteners | 6890
CM-103 | 2026-04-10 | J-2601 | 3310 | Material | Northgate Lumber Co | Drywall board, mud, tape | 1760
CM-104 | 2026-04-24 | J-2601 | 3300 | Subcontract | Vance Drywall Inc | Hang, tape, and finish kitchen | 5940
CM-105 | 2026-05-08 | J-2601 | 6100 | Subcontract | Arroyo Electric LLC | Rough-in and fixture setting | 8275
CM-106 | 2026-05-21 | J-2601 | 6200 | Subcontract | Bluewater Plumbing Co | Supply and rough plumbing | 7120
CM-107 | 2026-06-05 | J-2601 | 6000 | Material | Foxglove Cabinet Works | Cabinetry and countertop package | 19450
CM-108 | 2026-06-19 | J-2601 | 3400 | Subcontract | Selda Tile & Stone | Backsplash and floor tile setting | 4265
CM-109 | 2026-06-26 | J-2601 | 3410 | Material | Northgate Lumber Co | Tile and setting materials | 2070
CM-110 | 2026-06-30 | J-2601 | 5000 | Subcontract | Meridian Painting Co | Prime and paint kitchen | 3690
CM-111 | 2026-04-07 | J-2602 | 2100 | Subcontract | Carder Demolition LLC | Old deck removal and haul-off | 1485
CM-112 | 2026-04-14 | J-2602 | 2210 | Material | Northgate Lumber Co | Framing hardware and footing materials | 1240
CM-113 | 2026-04-18 | J-2602 | 2220 | Material | Cedarline Supply Inc | Cedar decking and railing | 7310
CM-114 | 2026-05-12 | J-2602 | 5000 | Subcontract | Meridian Painting Co | Sand and stain deck | 1655
CM-115 | 2026-05-08 | J-2603 | 2100 | Subcontract | Carder Demolition LLC | Bath demolition | 2290
CM-116 | 2026-05-15 | J-2603 | 2210 | Material | Northgate Lumber Co | Framing package | 1530
CM-117 | 2026-05-26 | J-2603 | 3200 | Subcontract | Ridge Foam & Insulation | Insulate walls and ceiling | 940
CM-118 | 2026-06-02 | J-2603 | 3300 | Subcontract | Vance Drywall Inc | Hang, tape, and finish bath | 3080
CM-119 | 2026-06-12 | J-2603 | 3310 | Material | Northgate Lumber Co | Board and mud for bath | 745
CM-120 | 2026-06-16 | J-2603 | 6100 | Subcontract | Arroyo Electric LLC | Bath circuits and fixtures | 4760
CM-121 | 2026-06-23 | J-2603 | 6200 | Subcontract | Bluewater Plumbing Co | Rough and trim plumbing | 7480
CM-122 | 2026-06-29 | J-2603 | 3400 | Subcontract | Selda Tile & Stone | Shower and floor tile | 6970

## Billings
Progress Billings (Draws, NET 30)
Invoice # | Date | Job # | Description | Amount | Due Date | Aging
INV-3001 | 2026-03-31 | J-2601 | Draw 1 - demo and framing complete | 24000 | 2026-04-30 | Past due
INV-3002 | 2026-04-30 | J-2601 | Draw 2 - mechanical rough-in | 30000 | 2026-05-30 | Past due
INV-3003 | 2026-06-30 | J-2601 | Draw 3 - cabinets and counters set | 28000 | 2026-07-30 | Current
INV-3004 | 2026-04-30 | J-2602 | Deck framing complete - 50 percent | 10000 | 2026-05-30 | Past due
INV-3005 | 2026-06-15 | J-2602 | Final bill - deck complete | 10000 | 2026-07-15 | Current
INV-3006 | 2026-05-31 | J-2603 | Draw 1 - demo and rough-in | 19500 | 2026-06-30 | Current
INV-3007 | 2026-06-30 | J-2603 | Draw 2 - drywall and mechanical | 14500 | 2026-07-30 | Current
Formulas:
Due Date = IF([Invoice #]="","",[Date]+30)

## Overhead
Overhead Pool & Allocation Rate (Mar-Jun 2026)
Item | Notes | Mar 2026 | Apr 2026 | May 2026 | Jun 2026 | Total
Shop & office rent | Studio yard and office | 1400 | 1400 | 1400 | 1400 | 5600
Trucks & equipment | Fuel, maintenance, small tool repairs | 850 | 850 | 850 | 850 | 3400
Insurance (GL & workers comp) | General liability and comp policies | 1150 | 1150 | 1150 | 1150 | 4600
ADMIN_LABOR | Office & admin labor, from Timesheets job OH | 240 | 240 | 240 | 240 | 960
Tools & job supplies | Blades, bits, consumables | 380 | 420 | 350 | 410 | 1560
Software & accounting | Estimating tools, bookkeeping, licenses | 260 | 260 | 260 | 260 | 1040
Marketing & bidding | Signage, referral gifts, plan takeoffs | 0 | 650 | 0 | 300 | 950
Total overhead pool | Sum of the monthly columns above | 4280 | 4970 | 4250 | 4610 | 18110
Direct costs incurred - all jobs | Job labor (Timesheets, job not OH) plus Cost Log, by month | 12960 | 19815 | 22790 | 53090 | 108655
Overhead rate (% of direct costs) | Pool divided by direct costs; applied in Job P&L column H |  |  |  |  | 16.67%

## WIP
Work in Progress & Percent Complete
Job # | Job Name | Contract Price | Est Cost | Costs to Date | % Complete | Earned Revenue | Billed to Date | Under/(Over) Billed | Billing Flag
J-2601 | Maple Kitchen Renovation | 96250 | 77000 | 66490 | 86.35% | 83112.5 | 82000 | 1112.5 | OK
J-2602 | Cedar Deck Replacement | 20000 | 16100 | 12990 | 80.68% | 16136.65 | 20000 | -3863.35 | Review billing
J-2603 | Primary Bath Suite Remodel | 49000 | 39200 | 29175 | 74.43% | 36468.75 | 34000 | 2468.75 | OK
All jobs |  | 165250 | 132300 | 108655 | 82.13% | 135717.9 | 136000 | -282.1

## Job P&L
Job P&L · Estimate vs Actual
Job # | Job Name | Status | Contract Price | Est Direct Cost | Actual Direct | Allocated Overhead | Total Cost | Direct Variance | Earned Revenue | Gross Profit to Date | GM % to Date | Margin Check
J-2601 | Maple Kitchen Renovation | Open | 96250 | 77000 | 66490 | 11082.1766 | 77572.1766 | -10510 | 83112.5 | 5540.32 | 6.666% | Below target
J-2602 | Cedar Deck Replacement | Open | 20000 | 16100 | 12990 | 2165.0996 | 15155.0996 | -3110 | 16136.65 | 981.55 | 6.083% | Below target
J-2603 | Primary Bath Suite Remodel | Open | 49000 | 39200 | 29175 | 4862.7238 | 34037.7238 | -10025 | 36468.75 | 2431.03 | 6.666% | Below target
All jobs |  |  | 165250 | 132300 | 108655 | 18110 | 126765 | -23645 | 135717.9 | 8952.9 | 6.597%

## Utilization
Utilization & Billing Summary
Code | Name | Role | Job Hours | Office Hours | Total Hours | % on Jobs | Labor Cost
E01 | Dana Whitfield | Owner & Project Lead | 11 | 0 | 11 | 100% | 660
E02 | Marcus Reed | Lead Carpenter | 44 | 0 | 44 | 100% | 1980
E03 | Sofia Nguyen | Carpenter | 37 | 0 | 37 | 100% | 1480
E04 | Tyler Brooks | Apprentice | 24 | 0 | 24 | 100% | 600
E05 | Priya Patel | Office & Bookkeeping | 0 | 32 | 32 | 0% | 960
E06 | Jamal Wright | Laborer & Site Support | 24 | 0 | 24 | 100% | 840
All crew |  |  | 140 | 32 | 172 | 81.4% | 6520